## Scope Matrix (2) (hidden)
Scope Matrix -Civil Works, 108.4 MW CCCP project at FREETOWN
Sr. No. | Description | Scope Division |  |  | Remarks
|  | SC (Sub- Contractor/ Vendor ) | SP-SPCPL Sierra Leone | (Agreed/Not Agreed)
SITE ESTABLISHMENT - TEMPORARY FACILITIES
1 | Accommodation & Food for Labour, Engineers and Supervisiors etc. Including all Facilities like Toilet ,Bathrooms, drinking water , Transportation Charges etc | √ |  |  | Accomodation.Food & Local Transportation shall be Sub-Contractors responsibility
2 | Establishment of Temporary Site office & Warehouse (Store) for Subcontractor's Materials and plant & Machinery | √ |  |  | Place Shall be Provided by SP-EPC. All materail required for construction of temporary site office and warehouse shall be under the scope of Sub- Contractor.
3 | Canteen, Restroom, shower room and toilets for labors and engineers within site premises as per site reuirement. | √ |  |  | Place Shall be Provided by SP-EPC. All materail required for construction of temporary Canteen, Restroom, shower room and toilets shall be under the scope of Sub- Contractor.
4 | Identification & development of area for storage of machinery | √
5 | Construction of Temporary access road, if required | √ |  |  | For Movement of machinary reuired for completion of works.
6 | Demolition of temporary facility built by the Subcontractor after work completion. | √ |  |  | Necessary completion certification from SP-EPC concerned Engineer to be obtained.
7 | Construction Power & its distribution | √ |  |  | Conractor shall endevor to provide construction power from the grid based on the availbility on chargable basis. However, Construction power and water shall be arranged by Sub contractor using its own sources without any additional cost to Contractor. Sub- Contractor to execute the network distribution (Water & Power) from the source point to various work location. Truck Mounted Rrequired quality Water Tanker shall be under Sub-Contractor Scope.To Maintain continuity of Water. Vendor shall arrange DG set as alternative.
8 | Construction Water & its distribution | √
9 | Supply and lnstallation of Energy Meter / Water Meter if required | √ |  |  | Sub-Contractor Scope
10 | Area lighting for contractor' identified areas including site off / stores etc. | √
11 | Drinking Water & Its distribution. | √ |  |  | Drinking water for own workmen shall be arrange by Sub Contractor. Water Test reports shall be submitted by the Sub-Contractor on periodic basis.
12 | Setting up First-Aid Facility at site | √ | √ |  | First Aid kit Shall be kept both by SPCL and Sub -Contractior
13 | Ingress and egress management (in cordination with the contractor) | √ | √
14 | PPE Washing assistance. | √
TOOLS / TACKLES (for Sub -Contractor' scope of work) Including Security)
1 | All Tools and tackles including crane/Farana, rebar cutting machine, rebar bending machine etc.complete in all respect) including transportation, unloading & ware housing, installation and operation at site. \Maintaenance of all the equipment and machinery. All TPI of Tools & Tcakles, machinery from relevant authority | √ |  |  | Sub - Contractor shall submit the list to SP-EPC with Testing Certificate and Fittness declartion.They shall aslo carry out peroidic inspection of the Euipments/ Machineries.
2 | Security for T&P, Machineries, Material, site office, stores etc. of their scope areas / works. | √ |  |  | Security for own office and own supplied material shall be in the scope of SC till completion of Project.
3 | Inspection & testing of equipment. | √ |  |  | Inspection & Testing whenever and wherever required.
INSURANCE/LICENSES/APPROVALS/STAUTORY COMPLIANACE (for contractor' scope of work execution)
1 | Workmen’s compensation | √ |  |  | Sub-Contractor scope, record to be submitted .
2 | Plant, Machinery and Automobile insuarance | √ |  |  | Automobile insuarance for the equipment mobilised by the Sub-Contractor
3 | Statutory Compliance | √ |  |  | Statutory Compiances like, social security, timely payment of wages, over time, Gender diversity, maintaining expatritiate proposition, work permits, holidays, medical chek-ups and other applicable compliances.
4 | Local Company registration | √ |  |  | All the Sub-contracting organisation shall be registered with Sierra Leone with valid construction permit.
5 | Tax Compliances | √ |  |  | Sub-Contractor to comply both direct and indirect taxation as per local laws.
SAFETY (for contractor' scope of work execution)
1 | HSE | √ |  |  | Sub-Contractor shall follow World Bank, IFC and Equator's Principle guidelines. Sub-Contractor to sign the HSE document.
2 | All safety gears such as Helmets , Hand gloves , Safety shoes ,Safety belts, Goggles etc required for the safety of all skilled / unskilled labours engaged by the contractor | √ |  |  | As per Employee and Site requirement.
3 | All barrication of places like excavation etc and other Critical areas must be hard barrication only. | √ |  |  | Sub-Contractor Scope
ADMINISTRATION (for contractor' scope of work execution)
1 | Security, Watch Guard at contractor' work space / storage yard etc. | √ |  |  | Sub-Contractor Scope
2 | Work Permit & Medical Formalties | √ |  |  | Sub-Contractor Scope
3 | Housekeeping at Work site | √ |  |  | Regular weekly house keeping work to be performed by the Sub -Contractor.
4 | Regular Maintenance of deployed machines / equipment | √ |  |  | Sub-Contractor Scope
5 | Overall quality control of Construction work | √ |  |  | Sub-Contractor Scope
6 | Local liasioning including govt. officials, if any | √ |  |  | SP-EPC to indicate Sub - Conhractor well in advance regarding any such Govt fees.
7 | Labour Statutories (Any applicable social securities) like PF, ESI, TDS etc | √ |  |  | Monthly Wages sheet to be provided by Sub-Contractor.
8 | Safety Officer & Stewards deployment | √
REPORTING/PROGRESS MONITORING (for all areas of execution)
1 | Machinery/ Manpower deployment schedule | √ |  |  | Area wise manpower deployment schedule to be submitted
2 | Monthly / Weekly / Daily work schedules ,work status & progress reports | √ |  |  | Daily, Weekly & Monthly
3 | Construction Schedule | √ | √ |  | L-2 schedule shall be provided by SP-EPC, Sub -Contractor has to submit L3 / L4 schedule - area wise - for approval. The subcontractor shall deploy resources in all necessary capacities to ensure the successful achievement of the contractor's milestones.
4 | Construction co-ordination procedure | √ |  |  | To be submitted by the Sub-Contractor within 7 days of receipt of LOA
SUPPLY - CIVIL CONSTRUCTION
1 | Ready Mix Concrete as per required Grade (RFC drgs) upto Site Location |  | √ |  | Contractor shall provide the concrete at desired pouring location. Concrete spreading, Ramping, Vibrating leveling, finishing, curing etc. as per drawings and directions of engineer incharge shall be in the scope of Subcontractor.
2 | Concrete Pumps/ Boom Placer for concrete placing at required place |  | √
3 | Placing of Concrete | √
4 | Cement Supply (other than RMC scope) | √
5 | Monthly submission of Reconcilliation statement for "Free issue material" - Concrete and Rebar | √ |  |  | Sub Contractor shall submit reconcillation statement on monthly basis.
6 | Reinforcement Bar (Raw Material) Supply |  | √ |  | Subcontrctor shall unload the material to contractor's store on arrival at site and based on the approved BBS and work requirement subcontractor shall get it issued from contractors. Transportation, bending, Cutting, placement, binding wire, cover block, etc. as per the approved BBS shall be in Subcontractors scope. Laps and chairs shall be measured saperately.
7 | Returning of "Scrap" qty | √ |  |  | Sub-Contractor to segregate the "Scrap qty" dia wise and stack properly at the identified area. ( If applicable )
8 | Shuttering material | √ |  |  | All types of shuttering material (either sub-structure or super structure items) shall be in Sub-Contractosr scope, Water proof plywood board shall be used, Quality shall be checked and approved by SP-EPC. Monthly inspection of all shuttering material shall be done by the contractor. All identified unusable/damages shuttering material shall be replaced by subcontractor at no extra cost.
9 | Steel-Scaffolding, Steel Pipes with steel clamps, Steel walkway planks/Gratings | √
10 | Stone Rubble for regular work item | √ |  |  | Sub-Contractor scope of work, however Quality shall be checked and approved by SPCPL
11 | Scaffolding & Boards | √
12 | Temporary materail required for Civil Works | √
13 | Seal Tape (Teflon Tapes etc.) | √
14 | Insulation Tape / Compound / Jointing Materials | √
15 | Oil / Lubricants | √
16 | Thermal Sticks / Temperature Recorders, if required | √
17 | Greases including Molycote Grease, if required | √
18 | Cleanings Solvent etc. | √
19 | Waste Cloth / rags, heisen cloth, curing compound. | √
20 | Other required materials of relevance other than those listed | √
21 | Dewater arrangement - | √ |  |  | Sub-Contractors to mobilize adequate resources like dewatering pumps as per requirement of required capacity. (working and standby).
22 | Disposal of surplus excavated soil as SP-EPC instruction | √
23 | Temporary Barricading | √ |  |  | Sub- Contractor Scope .Barricading to be done by means of metal sheet / structure support fencing as per the instructions of SPCPL EPC' safety engineers.
24 | Water Tanker | √ |  |  | Water tanker for dust controll.
25 | all general quality requirement shall be complied by subcontractor as per Quality Requirement annexure. | √
26 | Backfilling & compaction test | √ |  |  | Backfilling as per approved method statement and compaction test shall be performed bu subcontractor.

## Scope Matrix
Scope Matrix -Civil Works, 108.4 MW CCCP project at FREETOWN
Sr. No. | Description |  |  |  | Remarks
|  | SC | SP-SPCPL | Subcontractor Acceptance
|  | Subcontractor | Sierra Leone | (Yes/No)
SITE ESTABLISHMENT - TEMPORARY FACILITIES
1 | Accommodation & Food for Labour, Engineers and Supervisors etc. Including all Facilities like Toilet, Bathrooms, drinking water , Transportation Charges etc. | TRUE | FALSE |  | Accommodation. Food & Local Transportation shall be Sub-Contractors responsibility
2 | Establishment of Temporary Site office & Warehouse (Store) for Subcontractor's Materials and plant & Machinery. Pota Cabins or Containers. No Zinc Sheets shall be allowed | TRUE | FALSE |  | Place Shall be Provided by SP-EPC. All material required for the construction of temporary site office and warehouse shall be under the scope of Sub- Contractor.
3 | Canteen with solid floors and propoer ventilation ( No charcoal pit shall be allowed ), Restroom, shower room and toilets for labors and engineers within site premises as per site requirement. | TRUE | FALSE |  | Place Shall be Provided by SP-EPC. All material required for construction of temporary Canteen, Restroom, shower room and toilets shall be under the scope of Sub- Contractor.
4 | Identification & development of area for storage of machinery | TRUE | FALSE
5 | Construction of Temporary access road, if required | TRUE | FALSE |  | For Movement of machinery required for completion of works.
6 | Demolition of temporary facility built by the Subcontractor after work completion. | TRUE | FALSE |  | Necessary completion certification from SP-EPC concerned Engineer to be obtained.
7 | Construction Power & its distribution | TRUE | FALSE |  | Contractor shall endeavor to provide construction power from the grid based on the availability on chargeable basis. However, Construction power and water shall be arranged by Sub contractor using its own sources without any additional cost to Contractor. Sub- Contractor to execute the network distribution (Water & Power) from the source point to various work location.
8 | Construction Water & its distribution | TRUE | FALSE |  | Truck Mounted Required quality Water Tanker shall be under Sub-Contractor Scope. To Maintain continuity of Water. The subcontractor shall arrange DG set as alternative.
9 | Supply and installation of Energy Meter /Water Meter if required | TRUE | FALSE
10 | Area lighting for contractor' identified areas including site off / stores etc. | TRUE | FALSE
11 | Drinking Water & Its distribution. | TRUE | FALSE |  | Drinking water for own workmen shall be arrange by Subcontractor. Water Test reports shall be submitted by the Sub-Contractor on a periodic basis.
12 | Setting up First-Aid Facility at site | TRUE | TRUE |  | First Aid kit Shall be kept both by SPCL and Subcontractor
13 | Ingress and egress management (in coordination with the contractor). A propoer plan should be submitted for the workmen collection and entry to site. Large influx of manpower will not be allowed for entry | TRUE | TRUE
14 | PPE Washing assistance.Shower facilities should be made to ensire that workers can bathe before exiting the site. Also PPE washing should be ensured as the same shall be audited by Contrator | TRUE | FALSE
TOOLS / TACKLES (for Subcontractor' scope of work) Including Security) |  |  | FALSE
1 | All Tools and tackles including crane/Farana, rebar cutting machine, rebar bending machine etc. Complete in all respect) including transportation, unloading & ware housing, installation and operation at site. Maintenance of all the equipment and machinery. All TPI of Tools & Tackles, machinery from relevant authority | TRUE | FALSE |  | Subcontractor shall submit the list to SP-EPC with Testing Certificate and Fitness’ declaration and shall also carry out periodic inspection of the EQUIPMENTS/ Machineries.
2 | Security for T&P, Machineries, Material, site office, stores etc. of their scope areas / works. | TRUE | FALSE |  | Security for own office and own supplied material shall be in the scope of SC till completion of Project.
3 | Inspection & testing of equipment. | TRUE | FALSE |  | Inspection & testing whenever and wherever required.
INSURANCE/LICENSES/APPROVALS/STAUTORY COMPLIANACE (for contractor’s scope of work execution) |  |  | FALSE
1 | Workmen’s compensation | TRUE | FALSE |  | Sub-Contractor scope, record to be submitted.
2 | Plant, Machinery and Automobile insurance. | TRUE | FALSE |  | Automobile insurance for the equipment mobilized by the Sub-Contractor
3 | Statutory Compliance | TRUE | FALSE |  | Statutory Compliance like, social security, timely payment of wages, over time, Gender diversity, maintaining expatriate proposition, work permits, holidays, medical check-ups and other applicable compliances.
4 | Local Company registration | TRUE | FALSE |  | All the Sub-contracting organization shall be registered with Sierra Leone with valid construction permit.
5 | Tax Compliances | TRUE | FALSE |  | Sub-Contractor to comply with both direct and indirect taxation as per local laws.
SAFETY (for contractor’s scope of work execution) |  |  | FALSE
1 | HSE | TRUE | FALSE |  | Sub-Contractor shall follow World Bank, IFC and Equator's Principal guidelines. Sub-Contractor to sign the HSE document.
2 | All safety gears such as Helmets, Hand gloves , Safety shoes ,Safety belts, Goggles etc required for the safety of all skilled / unskilled labors engaged by the contractor | TRUE | FALSE |  | As per Employee and Site requirement.
3 | All barricading of places like excavation etc and other Critical areas must be hard barricading only. | TRUE | FALSE |  | Sub-Contractor Scope
ADMINISTRATION (for contractor' scope of work execution) |  |  | FALSE
1 | Security, Watch Guard at subcontractor' workspace / storage yard etc. | TRUE | FALSE |  | Sub-Contractor Scope
2 | Work Permit & Medical Formalities | TRUE | FALSE |  | Sub-Contractor Scope
3 | Housekeeping at Work site | TRUE | FALSE |  | Regular weekly housekeeping work to be performed by the Subcontractor.
4 | Regular Maintenance of deployed machines / equipment | TRUE | FALSE |  | Sub-Contractor Scope
5 | Overall quality control of Construction work | TRUE | FALSE |  | Sub-Contractor Scope
6 | Local lesioning including govt. officials, if any | TRUE | FALSE |  | SP-EPC to indicate Subcontractor well in advance regarding any such Govt fees.
7 | Labor Statutory (Any applicable social securities) like PF, ESI, TDS etc | TRUE | FALSE |  | Monthly Wages sheet to be provided by Sub-Contractor.
8 | Safety Officer & Stewards deployment | TRUE | FALSE
REPORTING/PROGRESS MONITORING (for all areas of execution) |  |  | FALSE
1 | Machinery/ Manpower deployment schedule | TRUE | FALSE |  | Area wise manpower deployment schedule to be submitted
2 | Monthly / Weekly / Daily work schedules, work status & progress reports | TRUE | FALSE |  | Daily, Weekly & Monthly
3 | Construction Schedule | TRUE | TRUE |  | L-2 schedule shall be provided by SP-EPC, Subcontractor has to submit L3 / L4 schedule - area wise - for approval. The subcontractor shall deploy resources in all necessary capacities to ensure the successful achievement of the contractor's milestones.
4 | Construction co-ordination procedure | TRUE | FALSE |  | To be submitted by the Sub-Contractor within 7 days of receipt of LOA
SUPPLY - CIVIL CONSTRUCTION |  |  | FALSE
1 | Ready Mix Concrete as per required Grade (RFC drgs) up to Site Location. Sub Contractor shall manage the waste concrete generated during the pouring propses and manage the waste | FALSE | TRUE |  | The contractor shall provide the concrete at desired pouring location. Concrete spreading, Ramping, Vibrating leveling, finishing, curing etc. as per drawings and directions of engineer in charge shall be in the scope of Subcontractor.
2 | Concrete Pumps/ Boom Placer for concrete placing at required place | FALSE | TRUE
3 | Placing of Concrete | TRUE | FALSE
4 | Cement Supply (other than RMC scope) | TRUE | FALSE
5 | Monthly submission of Reconciliation statement for "Free issue material" - Concrete and Rebar | TRUE | FALSE |  | Subcontractor shall submit reconciliation statement on monthly basis.
6 | Reinforcement Bar (Raw Material) Supply | FALSE | TRUE |  | Subcontrctor shall unload the material to contractor's store on arrival at site and based on the approved BBS and work requirement subcontractor shall get it issued from contractors. Transportation, bending, Cutting, placement, binding wire, cover block, etc. as per the approved BBS shall be in Subcontractors scope. Laps and chairs shall be measured separately.
7 | Returning of "Scrap" qty | TRUE | FALSE |  | Sub-Contractor to segregate the "Scrap qty" Dia wise and stack properly at the identified area. ( If applicable )
8 | Shuttering material ( The numbers of pours a plywood could be used will be limited to 3-4. Sub contractor shall provide the shuttering desing for Contractor review and approval for big and crirical pours | TRUE | FALSE |  | All types of shuttering material (either sub-structure or super structure items) shall be in Sucontractors scope, Water proof plywood board shall be used, Quality shall be checked and approved by SP-EPC. Monthly inspection of all shuttering material shall be done by the contractor. All identified unusable/damages shuttering material shall be replaced by subcontractor at no extra cost.
9 | Steel-Scaffolding, Steel Pipes with steel clamps, Steel walkway planks/Gratings | TRUE | FALSE
10 | Stone Rubble for regular work item | TRUE | FALSE |  | Sub-Contractor scope of work, however Quality shall be checked and approved by SPCPL
11 | Scaffolding & Boards. Wooden boards shall not be allowed. Sub Contractor shall provide the arrangment for scafolding & boards for Contractor review and approval | TRUE | FALSE
12 | Temporary material required for Civil Works | TRUE | FALSE
13 | Seal Tape (Teflon Tapes etc.) | TRUE | FALSE
14 | Insulation Tape / Compound / Jointing Materials | TRUE | FALSE
15 | Oil / Lubricants | TRUE | FALSE
16 | Thermal Sticks / Temperature Recorders, if required | TRUE | FALSE
17 | Greases including Molycote Grease, if required | TRUE | FALSE
18 | Cleanings Solvent etc. | TRUE | FALSE
19 | Waste Cloth / rags, heisen cloth, curing compound. | TRUE | FALSE
20 | Other required materials of relevance other than those listed | TRUE | FALSE
21 | Dewater arrangement - | TRUE | FALSE |  | Sub-Contractors to mobilize adequate resources like dewatering pumps as per requirement of required capacity. (working and standby).
22 | Disposal of surplus excavated soil as SP-EPC instruction | TRUE | FALSE
23 | Temporary Barricading | TRUE | FALSE |  | Sub- Contractor Scope. Barricading to be done by means of metal sheet / structure support fencing as per the instructions of SPCPL EPC' safety engineers.
24 | Water Tanker | TRUE | FALSE |  | Water tanker for dust control.
25 | all general quality requirements shall be complied by subcontractor as per Quality Requirement annexure. | TRUE | FALSE
26 | Backfilling & compaction test ( A third party lad shall be used for the verification of the tests. | TRUE | FALSE |  | Backfilling as per approved method statement and compaction test shall be performed bu subcontractor.